## Backlog
Backlog and Sprints
Item | Assignee | Date Assigned | Date Completed
Prototype ALU | Brad V | Feb 9th, 2018 | Feb 16th, 2018
Prototype Processor | Caiden K | Feb 9th, 2018 | Feb 16th, 2018
Prototype GUI | Emily S | Feb 9th, 2018 | Feb 23rd, 2018
Prototype Memory | Riley G | Feb 9th, 2018 | Feb 27th, 2018
Backlog and Sprints | Brad V and Riley G | Feb 9th, 2018 | Mar 3rd, 2018
Scrum Paper | Emily S | Feb 9th, 2018 | Feb 26th, 2018
Use Case Diagram | Brad V and Riley G | Feb 9th, 2018 | Feb 16th, 2018
Test Cases | Caiden K | Feb 9th, 2018 | Feb 16th, 2018
Meeting Log | Emily S | Feb 9th, 2018 | Feb 27th, 2018
Buttons don't re-enable after program's run | Emily S | Feb 24th, 2018 | Feb 27th, 2018
Convert Memory Input from "Null" to "+0000" | Caiden K | Feb 24th, 2018 | Feb 24th, 2018
Separate Accumulator and Memory | Caiden K | Feb 24th, 2018 | Feb 24th, 2018
Implement Read/Write Operations | Caiden K | Feb 24th, 2018 | Feb 24th, 2018
Set Accumulator function when called | Emily S | Feb 24th, 2018 | Feb 27th, 2018
Loop When Read Operation is Called Until Received | Caiden K | Feb 24th, 2018 | Feb 24th, 2018
Update ReceivedInput() to Utilize Func(T) | Caiden K | Feb 24th, 2018 | Feb 24th, 2018
Merge DisplayValue and Display Result Action(T) Properties | Brad V | Feb 24th, 2018 | Feb 24th, 2018
Add Output Console to MainForm | Emily S | Feb 24th, 2018 | Feb 27th, 2018
PromptUserForInput needs to pull +/-#### instead of ## | Emily S | Feb 25th, 2018 | Feb 27th, 2018
Update Test Case 2 to Accurately Test Scenario | Caiden K | Feb 27th, 2018 | Feb 27th, 2018